## 1b) Project Portfolio
PROJECT PORTFOLIO - LIST OF POTENTIAL PROJECTS AWAITING SIGN OFF, BUSINESS CASE ALREADY DRAFTED
Project ID | Potential Project/Programme | Business Area | Strategic Objective (order of importance in brackets) Quick ROI - within 6 months (1) Risk Avoidance/Regulatory (2) Improved Customer Experience (3) Longer ROI - 12 months + (4) | Additional Comments
P001 | National Marketing Campaign (Billboards & Bus Shelters) | Marketing | 4
P002 | Customer Loyalty Programme | Customer | 3
P003 | Warehouse Expansion Programme | Warehouse | 4 | Costly project with a long timeline, 24 month project
P004 | Data Protection Process Improvements | Audit | 2
P005 | CRM System | Customer | 3 | Costly project, requires integrations with web and app
P006 | Email Receipts | Customer | 1
P007 | Social Media Management Tool | Customer | 1
P008 | Finance Software Upgrade | Finance | 4
P009 | Warehouse AI System | Warehouse | 4
P010 | Till System Upgrade | Stores | 4

## 2) Kanban Board
KANBAN BOARD - APP REFRESH PROJECT
TO DO | IN PROGRESS | DONE | NEXT SPRINT | FUTURE WORK
Demo software in place
CRM fields created
Customer account creation - ability to save favourite products
Product numbers created in app
Payment (card) connected to finance system
Payment facility (card) implemented in app
Payment facility (paypal) implemented and connected to finance system
Extra product lines added to app
Store location software updated
Navigate any store using the app
BBC News live feed built into app
Social media feeds updated in app
Email collector for newsletter feed updated
Finance reporting feed developed
Finance reporting feed tested
QR code for product offers
App design complete UX
App design complete UI
App design A/B testing
Gaming built into app
App support process documented
App backup process documented (Disaster recovery)
App backup process tested (Disaster recovery)
App information security - features identified
App information security - features built
Sync with website in place

## 3) Risk Log
RISK LOG
Risk ID | Date Raised | Description (Cause & Effect - Clearly describe what the risk is and what the impact is) | Impact Rating (Enter 1-5) | Likelihood Rating (Enter 1-5) | Risk Score (Impact x Likelihood) | Action & Owner (What needs to happen to mitigate this risk or is it acceptable to do nothing at this stage?) | Target Action Completion Date (When will actions be completed by?) | Risk Owner (Who is responsible for mitigating this risk?) | Any Additional Comments / Any Escalation Required?
R001 |  |  |  |  | 0
R002 |  |  |  |  | 0
R003 |  |  |  |  | 0
R004 |  |  |  |  | 0
R005 |  |  |  |  | 0
R006 |  |  |  |  | 0
R007 |  |  |  |  | 0
R008 |  |  |  |  | 0
R009 |  |  |  |  | 0
R010 |  |  |  |  | 0
R011 |  |  |  |  | 0
R012 |  |  |  |  | 0
R013 |  |  |  |  | 0
R014 |  |  |  |  | 0
R015 |  |  |  |  | 0
R016 |  |  |  |  | 0
R017 |  |  |  |  | 0
R018 |  |  |  |  | 0
R019 |  |  |  |  | 0
R020 |  |  |  |  | 0
R021 |  |  |  |  | 0
R022 |  |  |  |  | 0
R023 |  |  |  |  | 0
R024 |  |  |  |  | 0
R025 |  |  |  |  | 0

## 4) Issue Log
ISSUE LOG
Risk ID | Date Raised | Description (Cause & Effect - Clearly describe what the issue is and what it is impacting - time, budget or quality) | Impact Rating (Enter 1-5) | Issue RAG | Action & Owner (What needs to happen to resolve this issue?) | Target Action Completion Date (When will actions be completed by?) | Issue Owner (Who is responsible for resolving this issue?) | Any Additional Comments / Any Escalation Required?
I001 |  |  |  | 0
I002 |  |  |  | 0
I003 |  |  |  | 0
I004 |  |  |  | 0
I005 |  |  |  | 0
I006 |  |  |  | 0
I007 |  |  |  | 0
I008 |  |  |  | 0
I009 |  |  |  | 0
I010 |  |  |  | 0
I011 |  |  |  | 0
I012 |  |  |  | 0
I013 |  |  |  | 0
I014 |  |  |  | 0
I015 |  |  |  | 0
I016 |  |  |  | 0
I017 |  |  |  | 0
I018 |  |  |  | 0
I019 |  |  |  | 0
I020 |  |  |  | 0
I021 |  |  |  | 0
I022 |  |  |  | 0
I023 |  |  |  | 0
I024 |  |  |  | 0
I025 |  |  |  | 0

## 5) Sprint 1 - Planned vs Actual
| Dev 1 | Dev 2 | Dev 3 | Dev 4 | Tester
Planned | 10 | 10 | 8 | 12 | 10
Actual | 5 | 10 | 8 | 20 | 11

## Risk Management Matrix
RISK MANAGEMENT MATRIX
IMPACT
|  | 1 - Very Low | 2 - Low | 3 - Medium | 4 - High | 5 - Very High
LIKELIHOOD | 5 - Very High
4 - High
3 - Medium
2 - Low
1 - Very Low